## Dashboard
FLOW METRICS + BURNDOWN DASHBOARD
SaaS Offshore JP ¦ 3 Dev · 2 QA · 1 PM ¦ Sprint 1W ¦ Capacity 70-75% ¦ TAT CA CONG THUC TU DONG
Moi so lieu tren Dashboard nay deu la CONG THUC doc tu cac sheet khac — KHONG CAN NHAP TAY. Tuong thich Google Sheets.
KEY PERFORMANCE INDICATORS — Tu dong tu Item Log + Weekly Data
TONG ITEMS |  |  | ITEMS DONE |  |  | WIP HIEN TAI |  | AVG THROUGHPUT |  |  | CYCLE TIME P85 |  |  | LITTLE'S LAW
48 |  |  | 36 |  |  | 12 |  | 5.7 |  |  | 10.75 |  |  | 2.1053
items du an |  |  | items hoan thanh |  |  | items dang xu ly |  | items / tuan |  |  | ngay (calendar) |  |  | ngay (WIP / Throughput)
Done: 36 ¦ Con: 12 |  |  | 75.0% completion |  |  | Dev: 3 ¦ QA: 8 ¦ Final: 1 |  | Min: 3 ¦ Max: 8 |  |  | P50: 9d ¦ Avg: 8.8d |  |  | CT du doan tu Dinh luat Little
TIEN DO DU AN | [5 empty] | CAPACITY & GIO |  |  |  |  | BURNDOWN STATUS
Chi So | Gia Tri (Cong Thuc) |  |  |  |  | Metric | Value |  |  |  | Metric | Value
Tong Items |  |  | 48 |  |  | Gross Hours/Tuan (3 Dev) |  | 120 |  |  | Tuan Hien Tai |  |  | 10
Items Done |  |  | 36 |  |  | Target 72.5% |  | 87 |  |  | Items Con Lai (Actual) |  |  | 12
Items Con Lai |  |  | 12 |  |  | Overhead 27.5% |  | 33 |  |  | Best Case (Ideal) |  |  | 0
% Done (Items) |  |  | 75% |  |  | Tong Gio Estimate |  | 888 |  |  | Worst Case (Buffer) |  |  | 10.1291
% Done (Gio) |  |  | 71.17% |  |  | Gio Done |  | 632 |  |  | Actual vs Best |  |  | 12
Tuan Hien Tai |  |  | 10 |  |  | Gio Con Lai |  | 256 |  |  | Actual vs Worst |  |  | 1.8709
Items Done Ly Tuong |  |  | 48 |  |  | Avg Gio / Item (Done) |  | 17.5556 |  |  | Burndown Zone |  |  | CHAM
Delta vs Ly Tuong |  |  | -12 |  |  | Tuan Con Lai (by Gio) |  | 2.9425 |  |  | Forecast 85% (tuan) |  |  | -3
WIP THEO TUNG BUOC — DEV + QA + FINAL (Cong thuc tu Item Log) | [7 empty] | THROUGHPUT & CYCLE TIME THEO TUAN (Cong thuc tu Weekly Data)
Buoc | Phase | WIP Hien Tai | Limit | Delta | Status | Reviewer |  | Tuan | Items Done | Gio Done | Tich Luy | Best | Actual | Worst | Status | CT Avg
Detail Design | Dev | 0 | -- | -- | -- |  |  | W01 | 6 | 108 | 7 | 43.2 | 41 | 46.102 | Nhanh | 6
Review Design | Dev | 0 | 2 | -2 | OK | Cross-review: Dev khac |  | W02 | 7 | 98 | 14 | 38.4 | 34 | 43.3265 | Nhanh | 6.5
Coding | Dev | 0 | 3 | -3 | OK | 1 Dev = 1 item |  | W03 | 7 | 119 | 21 | 33.6 | 27 | 40.083 | Nhanh | 6.6667
Review Code | Dev | 1 | 2 | -1 | OK | Cross-review: Dev khac |  | W04 | 3 | 51 | 24 | 28.8 | 24 | 36.4924 | Nhanh | 5.75
Whitebox | Dev | 2 | 2 | 0 | OK | Unit test boi Dev |  | W05 | 4 | 68 | 28 | 24 | 20 | 32.6196 | Nhanh | 5.25
Test Viewpoint | QA | 0 | -- | -- | -- |  |  | W06 | 8 | 152 | 36 | 19.2 | 12 | 28.5059 | Nhanh | 5.5
Test Cases | QA | 6 | 3 | 3 | OK |  |  | W07 | 8 | 96 | 44 | 14.4 | 4 | 24.1805 | Nhanh | 5.75
Review TC | QA | 0 | 2 | -2 | OK | Cross-review: QA khac |  | W08 | 7 | 84 | 51 | 9.6 | -3 | 19.665 | Nhanh | 6.75
Test Execute | QA | 2 | 3 | -1 | OK |  |  | W09 | 4 | 80 | 55 | 4.8 | -7 | 14.9767 | Nhanh | 6.75
Acceptance Test | Final | 0 | 2 | -2 | OK | Senior/Leader/PM |  | W10 | 3 | 57 | 58 | 0 | -10 | 10.1291 | Nhanh | 5.5
TONG WIP ACTIVE |  | 11 | 9 | 2 | VUOT LIMIT! | Stop nhan moi neu vuot 9
WIP Dev |  | 3
WIP QA |  | 8
WIP Final |  | 0
REVIEW BOTTLENECK — 3 Khau Review (Cong thuc tu Item Log) | [7 empty] | MONTE CARLO FORECAST & LITTLE'S LAW (Tu cac sheet)
Khau Review | WIP | Limit | Status | Avg Review Time | Reviews > 2d |  |  | Metric | Value |  | Don Vi |  | Ghi Chu
Review Design | 0 | 2 | OK | Dev_A | Dev_A |  |  | Items Con Lai |  | -10 |  | items |  | Tu Monte Carlo
Review Code | 1 | 2 | OK | Dev_B | Dev_A |  |  | Avg Throughput |  | 5.7 |  | items/w |  | Lich su
Review TC | 0 | 2 | OK | Dev_A | Dev_A |  |  | Forecast 50% |  | -2 |  | tuan |  | Xac suat 50:50
[8 empty] | Forecast 70% |  | -2 |  | tuan |  | Kha nang cao
[8 empty] | Forecast 85% (JP) |  | -3 |  | tuan |  | Cam ket JP — an toan
[8 empty] | Forecast 95% |  | -4 |  | tuan |  | Buffer 20%
[8 empty] | Little's Law CT |  | 1.4035 |  | ngay |  | WIP / Throughput
[8 empty] | CT Thuc Te (Avg) |  | 8.8333 |  | ngay |  | Tu Item Log
[8 empty] | Delta Little |  | 7.4298 |  | ngay |  | Duong = WIP an
QUY TRINH WORKFLOW — Dev → QA (Song Song) → Final → Done
DEV PIPELINE |  |  | Detail Design |  |  | → Review Design |  | → Coding |  |  | → Review Code |  |  | → Whitebox
QA PIPELINE |  |  | Test Viewpoint |  |  | → Test Cases |  | → Review TC |  |  | → Test Execute
FINAL |  |  | Acceptance Test |  |  | → DONE
QA chay SONG SONG voi Dev (bat dau tu khi Dev vao Coding). Review = nguoi KHAC (cross-review). Senior/Leader/PM lam Acceptance Test cuoi cung.

## Item Log
ITEM LOG — Nhat Ky Trang Thai Chi Tiet (Bang 3.1) ¦ Nhap NGAY chuyen trang thai → Cong thuc tu dong tinh
THONG TIN ITEM | [6 empty] | DEV PIPELINE (Ngay bat dau tung buoc) |  |  |  |  | QA PIPELINE (Song song) |  |  |  | FINAL |  | TU DONG TINH (CONG THUC)
Ma Item | Ten Hang Muc | Loai | Dev | QA | Reviewer | Gio UT | Detail Design | Review Design | Coding | Review Code | Whitebox | Test Viewpoint | Test Cases | Review TC | Test Execute | Accept Test | Done | Cycle Time | Lead Time | Trang Thai | Phase Hien Tai
ITM-001 | Bug: Task #1 | Bug | Dev_C | QA_2 | Dev_A | 24 | 2026-04-08 | 2026-04-10 | 2026-04-12 | 2026-04-15 | 2026-04-17 | 2026-04-13 | 2026-04-14 | 2026-04-16 | 2026-04-18 | 2026-04-19 | 2026-04-21 | 9 | 13 | Done | Done
ITM-002 | Feature: Task #2 | Feature | Dev_C | QA_2 | Dev_A | 24 | 2026-04-09 | 2026-04-11 | 2026-04-13 | 2026-04-17 | 2026-04-19 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 9 | 13 | Done | Done
ITM-003 | Spike: Task #3 | Spike | Dev_B | QA_1 | Dev_A | 8 | 2026-04-07 | 2026-04-08 | 2026-04-10 | 2026-04-12 | 2026-04-14 | 2026-04-11 | 2026-04-12 | 2026-04-14 | 2026-04-16 | 2026-04-19 | 2026-04-21 | 11 | 14 | Done | Done
ITM-004 | Bug: Task #4 | Bug | Dev_B | QA_2 | Dev_A | 32 | 2026-04-07 | 2026-04-09 | 2026-04-10 | 2026-04-13 | 2026-04-14 | 2026-04-11 | 2026-04-12 | 2026-04-14 | 2026-04-16 | 2026-04-17 | 2026-04-19 | 9 | 12 | Done | Done
ITM-005 | Bug: Task #5 | Bug | Dev_B | QA_2 | Dev_A | 24 | 2026-04-09 | 2026-04-11 | 2026-04-12 | 2026-04-15 | 2026-04-17 | 2026-04-12 | 2026-04-13 | 2026-04-15 | 2026-04-19 | 2026-04-22 | 2026-04-24 | 12 | 15 | Done | Done
ITM-006 | Feature: Task #6 | Feature | Dev_A | QA_2 | Dev_B | 16 | 2026-04-12 | 2026-04-13 | 2026-04-15 | 2026-04-17 | 2026-04-19 | 2026-04-15 | 2026-04-16 | 2026-04-18 | 2026-04-20 | 2026-04-21 | 2026-04-23 | 8 | 11 | Done | Done
ITM-007 | Feature: Task #7 | Feature | Dev_A | QA_1 | Dev_B | 8 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-15 | 2026-04-16 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 7 | 9 | Done | Done
ITM-008 | Bug: Task #8 | Bug | Dev_C | QA_2 | Dev_A | 16 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-17 | 2026-04-18 | 2026-04-15 | 2026-04-16 | 2026-04-18 | 2026-04-20 | 2026-04-23 | 2026-04-24 | 9 | 11 | Done | Done
ITM-009 | Feature: Task #9 | Feature | Dev_C | QA_2 | Dev_A | 12 | 2026-04-12 | 2026-04-14 | 2026-04-15 | 2026-04-17 | 2026-04-18 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-20 | 2026-04-22 | 2026-04-23 | 8 | 11 | Done | Done
ITM-010 | Feature: Task #10 | Feature | Dev_B | QA_2 | Dev_A | 8 | 2026-04-09 | 2026-04-11 | 2026-04-13 | 2026-04-15 | 2026-04-17 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-19 | 2026-04-21 | 2026-04-23 | 10 | 14 | Done | Done
ITM-011 | Spike: Task #11 | Spike | Dev_A | QA_1 | Dev_B | 4 | 2026-04-15 | 2026-04-17 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 6 | 10 | Done | Done
ITM-012 | Feature: Task #12 | Feature | Dev_C | QA_1 | Dev_A | 8 | 2026-04-15 | 2026-04-16 | 2026-04-18 | 2026-04-20 | 2026-04-21 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 6 | 9 | Done | Done
ITM-013 | Feature: Task #13 | Feature | Dev_B | QA_2 | Dev_A | 16 | 2026-04-15 | 2026-04-16 | 2026-04-18 | 2026-04-20 | 2026-04-21 | 2026-04-18 | 2026-04-19 | 2026-04-21 | 2026-04-23 | 2026-04-25 | 2026-04-27 | 9 | 12 | Done | Done
ITM-014 | Bug: Task #14 | Bug | Dev_B | QA_2 | Dev_A | 32 | 2026-04-13 | 2026-04-15 | 2026-04-17 | 2026-04-21 | 2026-04-22 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 9 | 13 | Done | Done
ITM-015 | Feature: Task #15 | Feature | Dev_B | QA_2 | Dev_A | 8 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-21 | 2026-04-24 | 2026-04-26 | 9 | 11 | Done | Done
ITM-016 | Feature: Task #16 | Feature | Dev_C | QA_1 | Dev_A | 24 | 2026-04-18 | 2026-04-20 | 2026-04-21 | 2026-04-23 | 2026-04-25 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 7 | 10 | Done | Done
ITM-017 | Feature: Task #17 | Feature | Dev_B | QA_1 | Dev_A | 32 | 2026-04-19 | 2026-04-20 | 2026-04-22 | 2026-04-26 | 2026-04-27 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-29 | 2026-05-01 | 2026-05-03 | 11 | 14 | Done | Done
ITM-018 | Feature: Task #18 | Feature | Dev_A | QA_2 | Dev_B | 8 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-26 | 7 | 9 | Done | Done
ITM-019 | Feature: Task #19 | Feature | Dev_B | QA_1 | Dev_A | 16 | 2026-04-17 | 2026-04-18 | 2026-04-20 | 2026-04-22 | 2026-04-23 | 2026-04-21 | 2026-04-22 | 2026-04-24 | 2026-04-25 | 2026-04-27 | 2026-04-29 | 9 | 12 | Done | Done
ITM-020 | Tech Debt: Task #20 | Tech Debt | Dev_C | QA_2 | Dev_A | 8 | 2026-04-16 | 2026-04-18 | 2026-04-20 | 2026-04-22 | 2026-04-23 | 2026-04-21 | 2026-04-22 | 2026-04-24 | 2026-04-25 | 2026-04-28 | 2026-04-29 | 9 | 13 | Done | Done
ITM-021 | Feature: Task #21 | Feature | Dev_B | QA_1 | Dev_A | 24 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-26 | 2026-04-27 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-28 | 2026-05-01 | 2026-05-03 | 11 | 13 | Done | Done
ITM-022 | Spike: Task #22 | Spike | Dev_A | QA_2 | Dev_B | 8 | 2026-04-20 | 2026-04-22 | 2026-04-24 | 2026-04-25 | 2026-04-27 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 6 | 10 | Done | Done
ITM-023 | Feature: Task #23 | Feature | Dev_A | QA_2 | Dev_B | 24 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-23 | 2026-04-25 | 2026-04-22 | 2026-04-23 | 2026-04-25 | 2026-04-27 | 2026-04-29 | 2026-04-30 | 9 | 11 | Done | Done
ITM-024 | Bug: Task #24 | Bug | Dev_C | QA_1 | Dev_A | 24 | 2026-04-20 | 2026-04-21 | 2026-04-23 | 2026-04-26 | 2026-04-28 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-29 | 2026-05-01 | 2026-05-02 | 9 | 12 | Done | Done
ITM-025 | Spike: Task #25 | Spike | Dev_C | QA_1 | Dev_A | 4 | 2026-04-21 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-27 | 2026-04-24 | 2026-04-25 | 2026-04-27 | 2026-04-29 | 2026-05-01 | 2026-05-03 | 9 | 12 | Done | Done
ITM-026 | Bug: Task #26 | Bug | Dev_B | QA_2 | Dev_A | 24 | 2026-04-25 | 2026-04-27 | 2026-04-28 | 2026-04-30 | 2026-05-02 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-03 | 2026-05-05 | 2026-05-07 | 9 | 12 | Done | Done
ITM-027 | Tech Debt: Task #27 | Tech Debt | Dev_A | QA_1 | Dev_B | 32 | 2026-04-22 | 2026-04-24 | 2026-04-26 | 2026-04-29 | 2026-04-30 | 2026-04-26 | 2026-04-27 | 2026-04-29 | 2026-05-01 | 2026-05-04 | 2026-05-05 | 9 | 13 | Done | Done
ITM-028 | Feature: Task #28 | Feature | Dev_B | QA_1 | Dev_A | 16 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-28 | 2026-04-30 | 2026-04-26 | 2026-04-27 | 2026-04-29 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 9 | 11 | Done | Done
ITM-029 | Feature: Task #29 | Feature | Dev_B | QA_2 | Dev_A | 12 | 2026-04-24 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-28 | 2026-04-29 | 2026-05-01 | 2026-05-02 | 2026-05-04 | 2026-05-05 | 8 | 11 | Done | Done
ITM-030 | Feature: Task #30 | Feature | Dev_C | QA_1 | Dev_A | 24 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-26 | 2026-04-27 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-30 | 2026-05-02 | 8 | 10 | Done | Done
ITM-031 | Feature: Task #31 | Feature | Dev_C | QA_1 | Dev_A | 12 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-03 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-05 | 2026-05-07 | 2026-05-09 | 9 | 11 | Done | Done
ITM-032 | Feature: Task #32 | Feature | Dev_B | QA_1 | Dev_A | 24 | 2026-04-26 | 2026-04-28 | 2026-04-29 | 2026-05-03 | 2026-05-04 | 2026-04-30 | 2026-05-01 | 2026-05-03 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 9 | 12 | Done | Done
ITM-033 | Feature: Task #33 | Feature | Dev_A | QA_2 | Dev_B | 32 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-05-02 | 2026-05-04 | 2026-04-29 | 2026-04-30 | 2026-05-02 | 2026-05-06 | 2026-05-08 | 2026-05-10 | 12 | 14 | Done | Done
ITM-034 | Bug: Task #34 | Bug | Dev_A | QA_2 | Dev_B | 12 | 2026-04-26 | 2026-04-28 | 2026-04-30 | 2026-05-01 | 2026-05-03 | 2026-04-30 | 2026-05-01 | 2026-05-03 | 2026-05-04 | 2026-05-07 | 2026-05-08 | 8 | 12 | Done | Done
ITM-035 | Bug: Task #35 | Bug | Dev_B | QA_2 | Dev_A | 16 | 2026-04-25 | 2026-04-27 | 2026-04-29 | 2026-05-01 | 2026-05-02 | 2026-04-29 | 2026-04-30 | 2026-05-02 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 7 | 11 | Done | Done
ITM-036 | Tech Debt: Task #36 | Tech Debt | Dev_B | QA_2 | Dev_A | 16 | 2026-04-30 | 2026-05-02 | 2026-05-03 | 2026-05-06 | 2026-05-08 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-10 | 2026-05-13 | 2026-05-15 | 12 | 15 | Done | Done
ITM-037 | Tech Debt: Task #37 | Tech Debt | Dev_C | QA_1 | Dev_A | 24 | 2026-04-29 | 2026-05-01 | 2026-05-02 | 2026-05-05 | 2026-05-06 | 2026-05-03 | 2026-05-04 | 2026-05-06 | 2026-05-07 |  |  |  |  | Test Execute | QA
ITM-038 | Bug: Task #38 | Bug | Dev_B | QA_2 | Dev_A | 32 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-05 | 2026-05-06 | 2026-05-01 | 2026-05-02 | [6 empty] | Test Cases | QA
ITM-039 | Bug: Task #39 | Bug | Dev_C | QA_2 | Dev_A | 24 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-03 | 2026-05-04 | 2026-05-01 | 2026-05-02 | [6 empty] | Test Cases | QA
ITM-040 | Tech Debt: Task #40 | Tech Debt | Dev_C | QA_2 | Dev_A | 8 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-06 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-08 | 2026-05-11 |  |  |  | Accept Test | Final
ITM-041 | Tech Debt: Task #41 | Tech Debt | Dev_C | QA_2 | Dev_A | 24 | 2026-05-02 | 2026-05-04 | 2026-05-06 | 2026-05-09 | 2026-05-11 | [8 empty] | Whitebox | Dev
ITM-042 | Feature: Task #42 | Feature | Dev_B | QA_2 | Dev_A | 8 | 2026-05-02 | 2026-05-03 | 2026-05-05 | 2026-05-06 | 2026-05-08 | 2026-05-05 | 2026-05-06 | [6 empty] | Test Cases | QA
ITM-043 | Feature: Task #43 | Feature | Dev_C | QA_1 | Dev_A | 16 | 2026-05-04 | 2026-05-06 | 2026-05-08 | 2026-05-10 | 2026-05-12 | 2026-05-08 | 2026-05-09 | [6 empty] | Test Cases | QA
ITM-044 | Tech Debt: Task #44 | Tech Debt | Dev_C | QA_2 | Dev_A | 32 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-08 | 2026-05-09 | 2026-05-05 | 2026-05-06 | [6 empty] | Test Cases | QA
ITM-045 | Spike: Task #45 | Spike | Dev_A | QA_2 | Dev_B | 8 | 2026-05-03 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-06 | 2026-05-07 | [6 empty] | Test Cases | QA
ITM-046 | Bug: Task #46 | Bug | Dev_B | QA_1 | Dev_A | 32 | 2026-05-04 | 2026-05-06 | 2026-05-07 | 2026-05-11 | 2026-05-12 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-13 |  |  |  |  | Test Execute | QA
ITM-047 | Feature: Task #47 | Feature | Dev_C | QA_2 | Dev_A | 24 | 2026-05-05 | 2026-05-07 | 2026-05-08 | 2026-05-12 | 2026-05-14 | [8 empty] | Whitebox | Dev
ITM-048 | Feature: Task #48 | Feature | Dev_C | QA_1 | Dev_A | 24 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-09 | [9 empty] | Review Code | Dev
THONG KE TU DONG (TAT CA LA CONG THUC)
Tong Items |  |  |  |  | 48
Items Done |  |  |  |  | 36
Items Dang Dev |  |  |  |  | 3
Items Dang QA |  |  |  |  | 8
Items Dang Final |  |  |  |  | 1
Items Backlog |  |  |  |  | 0
Avg Cycle Time
Max Cycle Time |  |  |  |  | 12
Min Cycle Time |  |  |  |  | 6
Avg Lead Time |  |  |  |  | 11.8333
Tong Gio Estimate |  |  |  |  | 888
Gio Done |  |  |  |  | 632
Gio Con Lai |  |  |  |  | 256
% Done (Items) |  |  |  |  | 75%
% Done (Gio) |  |  |  |  | 71.17%
WIP THEO TUNG BUOC (CONG THUC TU DONG)
Buoc | WIP Hien Tai | Phase | Recommend Limit
Detail Design | 0 | Dev | --
Review Design | 0 | Dev | 2
Coding | 0 | Dev | 3
Review Code | 1 | Dev | 2
Whitebox | 2 | Dev | 2
Test Viewpoint | 0 | QA | --
Test Cases | 6 | QA | 3
Review TC | 0 | QA | 2
Test Execute | 2 | QA | 3
Acceptance Test | 0 | Final | 2

## Daily WIP
DAILY WIP TRACKER — Theo Doi HANG NGAY ¦ PM dien cuoi moi ngay lam viec
Huong dan: Moi ngay cuoi gio, dem so items o tung stage va dien vao. Cong thuc tu dong tinh WIP, status, canh bao.
|  | DEV PIPELINE |  |  |  |  | QA PIPELINE | [5 empty] | TU DONG (CONG THUC)
Ngay | Thu | Detail Design | Rev Design | Coding | Rev Code | Whitebox | Test VP | Test Cases | Rev TC | Test Exec | Accept Test | Done | WIP Dev | WIP QA | WIP Total
LIMIT |  | -- | 2 | 3 | 2 | 2 | -- | 3 | 2 | 3 | 2 | --
2026-04-06 | T2 | 4 | 2 | 2 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 8 | 5 | 13
2026-04-07 | T3 | 3 | 0 | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 0 | 2 | 9 | 7 | 16
2026-04-08 | T4 | 3 | 2 | 3 | 1 | 2 | 2 | 2 | 0 | 1 | 2 | 4 | 11 | 5 | 18
2026-04-09 | T5 | 2 | 0 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 0 | 6 | 6 | 8 | 14
2026-04-10 | T6 | 2 | 0 | 3 | 1 | 0 | 1 | 1 | 2 | 1 | 2 | 8 | 6 | 5 | 13
2026-04-13 | T2 | 3 | 1 | 3 | 1 | 1 | 0 | 2 | 2 | 2 | 1 | 10 | 9 | 6 | 16
2026-04-14 | T3 | 3 | 1 | 1 | 0 | 0 | 2 | 1 | 1 | 2 | 1 | 12 | 5 | 6 | 12
2026-04-15 | T4 | 1 | 2 | 3 | 2 | 1 | 1 | 3 | 0 | 2 | 1 | 14 | 9 | 6 | 16
2026-04-16 | T5 | 3 | 2 | 3 | 2 | 0 | 1 | 2 | 0 | 1 | 2 | 16 | 10 | 4 | 16
2026-04-17 | T6 | 1 | 0 | 3 | 1 | 2 | 0 | 2 | 2 | 3 | 1 | 18 | 7 | 7 | 15
2026-04-20 | T2 | 4 | 2 | 1 | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 20 | 8 | 3 | 11
2026-04-21 | T3 | 2 | 2 | 2 | 0 | 0 | 2 | 1 | 2 | 3 | 0 | 22 | 6 | 8 | 14
2026-04-22 | T4 | 3 | 2 | 1 | 1 | 1 | 0 | 2 | 2 | 2 | 2 | 24 | 8 | 6 | 16
2026-04-23 | T5 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 26 | 7 | 4 | 13
2026-04-24 | T6 | 2 | 1 | 1 | 0 | 2 | 1 | 3 | 1 | 2 | 2 | 28 | 6 | 7 | 15
2026-04-27 | T2 | 1 | 1 | 1 | 1 | 2 | 0 | 3 | 1 | 1 | 1 | 30 | 6 | 5 | 12
2026-04-28 | T3 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 0 | 2 | 2 | 32 | 8 | 7 | 17
2026-04-29 | T4 | 2 | 2 | 1 | 2 | 1 | 0 | 3 | 0 | 3 | 0 | 34 | 8 | 6 | 14
2026-04-30 | T5 | 4 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 36 | 7 | 3 | 10
2026-05-01 | T6 | 3 | 0 | 3 | 1 | 1 | 0 | 2 | 0 | 1 | 0 | 36 | 8 | 3 | 11
2026-05-04 | T2 | 1 | 1 | 3 | 2 | 0 | 1 | 3 | 1 | 3 | 2 | 36 | 7 | 8 | 17
2026-05-05 | T3 | 1 | 0 | 3 | 2 | 1 | 0 | 2 | 0 | 1 | 2 | 36 | 7 | 3 | 12
2026-05-06 | T4 | 1 | 1 | 1 | 0 | 1 | 2 | 3 | 0 | 2 | 1 | 36 | 4 | 7 | 12
2026-05-07 | T5 | 1 | 2 | 3 | 2 | 0 | 2 | 3 | 2 | 3 | 2 | 36 | 8 | 10 | 20
2026-05-08 | T6 | 2 | 1 | 1 | 2 | 1 | 0 | 3 | 1 | 2 | 0 | 36 | 7 | 6 | 13
CANH BAO TU DONG (CONG THUC)
Rev Design vuot limit? |  |  | OK |  |  | Review Design WIP > 2
Rev Code vuot limit? |  |  | OK |  |  | Review Code WIP > 2 = bottleneck
Coding vuot limit? |  |  | OK |  |  | Coding WIP > 3
Rev TC vuot limit? |  |  | OK |  |  | Review TC WIP > 2
Total WIP vuot 9? |  |  | ⚠ VUOT — Max: 20 |  |  | Tong WIP > 9 = flow nghen
Avg WIP/ngay |  |  | 14.24 |  |  | Nen < 9 de flow on dinh

## Weekly Data
DU LIEU TONG HOP THEO TUAN ¦ PM cap nhat moi Thu Sau ¦ 5 BIEU DO tu dong
Cot A-H: NHAP TAY ¦ Cot I tro di: TAT CA LA CONG THUC TU DONG ¦ Tuong thich Google Sheets
|  | NHAP: WIP CUOI TUAN |  |  | NHAP: KET QUA TUAN |  |  | TU DONG TINH (CONG THUC — KHONG SUA)
Tuan | Ngay Thu 6 | WIP Dev | WIP QA | WIP Final | Items Done (tuan nay) | Gio Done (tuan nay) | Items Done Tich Luy | WIP Total | Items Con Lai | Best Case | Worst Case | Throughput Avg (4w) | Delta TP vs Prev | Gio Con Lai | % Done Items | % Done Gio | Status | WIP Limit(9)
W01 | 2026-04-10 | 4 | 2 | 0 | 6 | 108 | 7 | 6 | 41 | 43.2 | 46.102 | 6 | 0 | 660 | 14.58% | 14.06% | Nhanh | 9
W02 | 2026-04-17 | 3 | 3 | 2 | 7 | 98 | 14 | 8 | 34 | 38.4 | 43.3265 | 6.5 | 1 | 562 | 29.17% | 26.82% | Nhanh | 9
W03 | 2026-04-24 | 4 | 4 | 0 | 7 | 119 | 21 | 8 | 27 | 33.6 | 40.083 | 6.6667 | 0 | 443 | 43.75% | 42.32% | Nhanh | 9
W04 | 2026-05-01 | 4 | 3 | 0 | 3 | 51 | 24 | 7 | 24 | 28.8 | 36.4924 | 5.75 | -4 | 392 | 50% | 48.96% | Nhanh | 9
W05 | 2026-05-08 | 4 | 3 | 2 | 4 | 68 | 28 | 9 | 20 | 24 | 32.6196 | 5.25 | 1 | 324 | 58.33% | 57.81% | Nhanh | 9
W06 | 2026-05-15 | 3 | 3 | 0 | 8 | 152 | 36 | 6 | 12 | 19.2 | 28.5059 | 5.5 | 4 | 172 | 75% | 77.6% | Nhanh | 9
W07 | 2026-05-22 | 5 | 2 | 2 | 8 | 96 | 44 | 9 | 4 | 14.4 | 24.1805 | 5.75 | 0 | 76 | 91.67% | 90.1% | Nhanh | 9
W08 | 2026-05-29 | 4 | 3 | 2 | 7 | 84 | 51 | 9 | -3 | 9.6 | 19.665 | 6.75 | -1 | -8 | 106.2% | 101% | Nhanh | 9
W09 | 2026-06-05 | 4 | 4 | 1 | 4 | 80 | 55 | 9 | -7 | 4.8 | 14.9767 | 6.75 | -3 | -88 | 114.6% | 111.5% | Nhanh | 9
W10 | 2026-06-12 | 4 | 3 | 1 | 3 | 57 | 58 | 8 | -10 | 0 | 10.1291 | 5.5 | -1 | -145 | 120.8% | 118.9% | Nhanh | 9

## Cycle Time
CYCLE TIME ANALYSIS ¦ Tinh tu Item Log bang cong thuc
PERCENTILE (CONG THUC TU 'Item Log')
Metric | Value (ngay)
P50 (Median) |  |  | 9
P70 |  |  | 9
P85 |  |  | 10.75
P95 |  |  | 12
Average |  |  | 8.8333
Max |  |  | 12
Min |  |  | 6
CYCLE TIME THEO LOAI ITEM (CONG THUC)
Loai | Count | Avg CT | P85 | Min CT | Max CT
Feature | 20 | 8.75
Bug | 9 | 9
Tech Debt | 3 | 10
Spike | 4 | 8
CYCLE TIME THEO DEV (CONG THUC)
Dev | Count | Avg CT | P85 | Min | Max
Dev_A | 9 | 8
Dev_B | 16 | 9.625
Dev_C | 11 | 8.3636
PHAN PHOI CT
Range | Count
1-3d | 0
4-6d | 3
7-9d | 26
10-12d | 7
13d+ | 0

## Monte Carlo
MONTE CARLO FORECAST ¦ Cong thuc doc tu Weekly Data
INPUTS (Cong thuc tu dong tu cac sheet khac)
Items con lai |  |  | -10 | items
Avg Throughput |  |  | 5.7 | items/tuan
Min Throughput |  |  | 3 | items/tuan
Max Throughput |  |  | 8 | items/tuan
Tuan da qua |  |  | 10 | tuan
FORECAST (CONG THUC)
Confidence | Tuan Can | Cong Thuc | Giai Thich
50% (Trung binh) | -2 | Items / Avg TP |  | Xac suat 50:50
70% | -2 | Items / ((Avg+Min)/2) |  | Kha nang cao
85% (Cam ket JP) | -3 | Items / Min TP |  | An toan nhat
95% | -4 | Items / Min TP * 1.2 |  | Buffer 20%
LITTLE'S LAW CHECK (CONG THUC)
WIP Hien Tai | 8 | Tu Weekly Data
Avg Throughput | 5.7 | Tu tren
CT Du Doan (WIP/TP) | 1.4035 | Dinh luat Little
CT Thuc Te (Avg) | 8.8333 | Tu Item Log
Delta | 7.4298 | Duong=WIP an ¦ Am=flow tot
Status | Co WIP an/bottleneck

## Review Tracker
REVIEW TRACKER ¦ Review Design + Review Code + Review TC ¦ Bottleneck Focus
3 khau Review la BOTTLENECK lon nhat: Review Design (WIP=2), Review Code (WIP=2), Review TC (WIP=2). Quy tac: REVIEW TRUOC, CODE SAU. Reviewer la nguoi khac (cross-review).
Ma Item | Loai | Implementer | Reviewer | Review Type | Ngay Bat Dau | Ngay Xong | Thoi Gian (ngay) | Status
ITM-003 | Spike | Dev_B | Dev_A | Rev Design | 2026-04-08 | 2026-04-10 | 2 | Done
ITM-004 | Bug | Dev_B | Dev_A | Rev Design | 2026-04-09 | 2026-04-10 | 1 | Done
ITM-001 | Bug | Dev_C | Dev_A | Rev Design | 2026-04-10 | 2026-04-12 | 2 | Done
ITM-002 | Feature | Dev_C | Dev_A | Rev Design | 2026-04-11 | 2026-04-13 | 2 | Done
ITM-005 | Bug | Dev_B | Dev_A | Rev Design | 2026-04-11 | 2026-04-12 | 1 | Done
ITM-010 | Feature | Dev_B | Dev_A | Rev Design | 2026-04-11 | 2026-04-13 | 2 | Done
ITM-003 | Spike | Dev_B | Dev_A | Rev Code | 2026-04-12 | 2026-04-14 | 2 | Done
ITM-004 | Bug | Dev_B | Dev_A | Rev Code | 2026-04-13 | 2026-04-14 | 1 | Done
ITM-006 | Feature | Dev_A | Dev_B | Rev Design | 2026-04-13 | 2026-04-15 | 2 | Done
ITM-007 | Feature | Dev_A | Dev_B | Rev Design | 2026-04-13 | 2026-04-14 | 1 | Done
ITM-003 | Spike | QA_1 | QA_2 | Rev TC | 2026-04-14 | 2026-04-16 | 2 | Done
ITM-004 | Bug | QA_2 | QA_1 | Rev TC | 2026-04-14 | 2026-04-16 | 2 | Done
ITM-008 | Bug | Dev_C | Dev_A | Rev Design | 2026-04-14 | 2026-04-15 | 1 | Done
ITM-009 | Feature | Dev_C | Dev_A | Rev Design | 2026-04-14 | 2026-04-15 | 1 | Done
ITM-001 | Bug | Dev_C | Dev_A | Rev Code | 2026-04-15 | 2026-04-17 | 2 | Done
ITM-002 | Feature | QA_2 | QA_1 | Rev TC | 2026-04-15 | 2026-04-20 | 5 | Done
ITM-005 | Bug | Dev_B | Dev_A | Rev Code | 2026-04-15 | 2026-04-17 | 2 | Done
ITM-005 | Bug | QA_2 | QA_1 | Rev TC | 2026-04-15 | 2026-04-19 | 4 | Done
ITM-007 | Feature | Dev_A | Dev_B | Rev Code | 2026-04-15 | 2026-04-16 | 1 | Done
ITM-010 | Feature | Dev_B | Dev_A | Rev Code | 2026-04-15 | 2026-04-17 | 2 | Done
ITM-014 | Bug | Dev_B | Dev_A | Rev Design | 2026-04-15 | 2026-04-17 | 2 | Done
ITM-001 | Bug | QA_2 | QA_1 | Rev TC | 2026-04-16 | 2026-04-18 | 2 | Done
ITM-010 | Feature | QA_2 | QA_1 | Rev TC | 2026-04-16 | 2026-04-19 | 3 | Done
ITM-012 | Feature | Dev_C | Dev_A | Rev Design | 2026-04-16 | 2026-04-18 | 2 | Done
ITM-013 | Feature | Dev_B | Dev_A | Rev Design | 2026-04-16 | 2026-04-18 | 2 | Done
ITM-015 | Feature | Dev_B | Dev_A | Rev Design | 2026-04-16 | 2026-04-17 | 1 | Done
ITM-002 | Feature | Dev_C | Dev_A | Rev Code | 2026-04-17 | 2026-04-19 | 2 | Done
ITM-006 | Feature | Dev_A | Dev_B | Rev Code | 2026-04-17 | 2026-04-19 | 2 | Done
ITM-008 | Bug | Dev_C | Dev_A | Rev Code | 2026-04-17 | 2026-04-18 | 1 | Done
ITM-009 | Feature | Dev_C | Dev_A | Rev Code | 2026-04-17 | 2026-04-18 | 1 | Done
ITM-009 | Feature | QA_2 | QA_1 | Rev TC | 2026-04-17 | 2026-04-20 | 3 | Done
ITM-011 | Spike | Dev_A | Dev_B | Rev Design | 2026-04-17 | 2026-04-19 | 2 | Done
ITM-006 | Feature | QA_2 | QA_1 | Rev TC | 2026-04-18 | 2026-04-20 | 2 | Done
ITM-007 | Feature | QA_1 | QA_2 | Rev TC | 2026-04-18 | 2026-04-19 | 1 | Done
ITM-008 | Bug | QA_2 | QA_1 | Rev TC | 2026-04-18 | 2026-04-20 | 2 | Done
ITM-015 | Feature | Dev_B | Dev_A | Rev Code | 2026-04-18 | 2026-04-19 | 1 | Done
ITM-018 | Feature | Dev_A | Dev_B | Rev Design | 2026-04-18 | 2026-04-19 | 1 | Done
ITM-019 | Feature | Dev_B | Dev_A | Rev Design | 2026-04-18 | 2026-04-20 | 2 | Done
ITM-020 | Tech Debt | Dev_C | Dev_A | Rev Design | 2026-04-18 | 2026-04-20 | 2 | Done
ITM-014 | Bug | QA_2 | QA_1 | Rev TC | 2026-04-19 | 2026-04-24 | 5 | Done
ITM-015 | Feature | QA_2 | QA_1 | Rev TC | 2026-04-19 | 2026-04-21 | 2 | Done
ITM-011 | Spike | Dev_A | Dev_B | Rev Code | 2026-04-20 | 2026-04-21 | 1 | Done
ITM-012 | Feature | Dev_C | Dev_A | Rev Code | 2026-04-20 | 2026-04-21 | 1 | Done
ITM-012 | Feature | QA_1 | QA_2 | Rev TC | 2026-04-20 | 2026-04-22 | 2 | Done
ITM-013 | Feature | Dev_B | Dev_A | Rev Code | 2026-04-20 | 2026-04-21 | 1 | Done
ITM-016 | Feature | Dev_C | Dev_A | Rev Design | 2026-04-20 | 2026-04-21 | 1 | Done
ITM-017 | Feature | Dev_B | Dev_A | Rev Design | 2026-04-20 | 2026-04-22 | 2 | Done
ITM-018 | Feature | Dev_A | Dev_B | Rev Code | 2026-04-20 | 2026-04-21 | 1 | Done
ITM-023 | Feature | Dev_A | Dev_B | Rev Design | 2026-04-20 | 2026-04-21 | 1 | Done
ITM-013 | Feature | QA_2 | QA_1 | Rev TC | 2026-04-21 | 2026-04-23 | 2 | Done
ITM-014 | Bug | Dev_B | Dev_A | Rev Code | 2026-04-21 | 2026-04-22 | 1 | Done
ITM-021 | Feature | Dev_B | Dev_A | Rev Design | 2026-04-21 | 2026-04-22 | 1 | Done
ITM-024 | Bug | Dev_C | Dev_A | Rev Design | 2026-04-21 | 2026-04-23 | 2 | Done
ITM-011 | Spike | QA_1 | QA_2 | Rev TC | 2026-04-22 | 2026-04-23 | 1 | Done
ITM-018 | Feature | QA_2 | QA_1 | Rev TC | 2026-04-22 | 2026-04-23 | 1 | Done
ITM-019 | Feature | Dev_B | Dev_A | Rev Code | 2026-04-22 | 2026-04-23 | 1 | Done
ITM-020 | Tech Debt | Dev_C | Dev_A | Rev Code | 2026-04-22 | 2026-04-23 | 1 | Done
ITM-022 | Spike | Dev_A | Dev_B | Rev Design | 2026-04-22 | 2026-04-24 | 2 | Done
ITM-016 | Feature | Dev_C | Dev_A | Rev Code | 2026-04-23 | 2026-04-25 | 2 | Done
ITM-023 | Feature | Dev_A | Dev_B | Rev Code | 2026-04-23 | 2026-04-25 | 2 | Done
THONG KE REVIEW
Tong Reviews |  |  | 60
Avg Review Time |  |  | 1.75
Reviews > 2 ngay |  |  | 5
Dang Cho Review |  |  | 0

## Huong Dan
HUONG DAN SU DUNG — GOOGLE SHEETS COMPATIBLE
QUY TRINH THUC TE
DEV: Detail Design → Review Design → Coding → Review Code → Whitebox (Unit Test)
QA : Test Viewpoint → Test Cases → Review TC → Test Execute (chay song song voi Dev)
FINAL: Acceptance Test (Senior/Leader/PM) → Done
REVIEWER: Nguoi KHAC (review cheo) — Dev_A code thi Dev_B review, QA_1 viet TC thi QA_2 review
Item Log (NGAY)
Nhap NGAY CHINH XAC khi item chuyen sang buoc moi. VD: bat dau Coding → dien ngay vao cot J
Cycle Time, Lead Time, Trang Thai, Phase = TU DONG TINH bang cong thuc
WIP tung buoc = TU DONG DEM bang COUNTIF
Gio Uoc Tinh de bao cao JP. KHONG dung de forecast (dung Throughput thay the)
Daily WIP (NGAY)
MOI NGAY cuoi gio: dem so items DANG NAM o tung buoc tren board, dien vao
Cot WIP Dev, WIP QA, WIP Total = CONG THUC tu dong
O DO = vuot WIP limit. PM can: dung nhan moi, hoan thanh truoc, ho tro review
Canh bao tu dong o duoi bang: Review bottleneck, WIP vuot limit
Weekly Data + 5 BIEU DO (TUAN)
MOI THU SAU: dien 6 o (WIP Dev, WIP QA, WIP Final, Items Done, Gio Done, Tich Luy)
TAT CA 12 cot con lai = CONG THUC TU DONG. KHONG SUA.
BURNDOWN 3 DUONG: Xanh la (Best) ¦ Xanh dam (Actual) ¦ Do (Worst+Buffer)
Actual nam giua Best va Worst = DU AN OK
Actual vuot tren Worst = CHAM — can hanh dong ngay
CFD: Dai WIP Dev/QA/Final phang to = bottleneck o phase do
THROUGHPUT: Cot items done + duong rolling avg 4 tuan
WIP CHART: Cot chong 3 phase + duong limit do = 9
GIO BURNDOWN: Gio con lai giam dan — gui JP hang tuan
Cycle Time (TU DONG)
TAT CA la cong thuc doc tu Item Log. Khong can nhap gi
Percentile, phan phoi, theo loai, theo dev = tu dong
Cot P85 va histogram giup nhan biet xu huong
Monte Carlo & Little's Law (TU DONG)
Doc tu Weekly Data va Item Log. Forecast 50/70/85/95%
Dung 85% cam ket JP. Little's Law kiem tra WIP an
Review Tracker (BOTTLENECK)
3 khau Review la nguyen nhan chinh gay cham: Rev Design, Rev Code, Rev TC
WIP Limit = 2 cho moi khau review. Vuot = DUNG LAI, REVIEW TRUOC
Review > 2 ngay = canh bao. PM escalate ngay
IMPORT VAO GOOGLE SHEETS
Buoc 1: Upload file .xlsx nay len Google Drive
Buoc 2: Mo bang Google Sheets (tu dong convert)
Buoc 3: Kiem tra cong thuc hoat dong (thu thay doi 1 ngay trong Item Log → Cycle Time tu cap nhat)
Buoc 4: Tao chart trong Google Sheets tu sheet Weekly Data (Select data → Insert → Chart)
Luu y: PERCENTILE.INC trong GSheets la PERCENTILE. AVERAGEIFS, COUNTIFS, SUMPRODUCT deu work.
Luu y: Array formula MIN(IF(...)) can Ctrl+Shift+Enter trong GSheets hoac dung MINIFS thay the